## projetos
Projeto | Descrição | Orçamento | Data Aprovação | Data de Conclusão | Data Última Atualização | Status | Gerente Projeto | Equipe | Horas Trabalhadas
PROJ-20-3000 | Manutenção Motores | 620000 | 2020-01-10 | 2020-12-25 | 2020-12-30 | Finalizado | Mauricio L. | 5 | 12000
PROJ-20-3001 | Manutenção Paineis | 500000 | 2020-01-05 | 2020-12-25 | 2020-12-30 | Finalizado | Gustavo A. | 8 | 19200
PROJ-20-3002 | Manutenção Embarcação | 1010000 | 2020-01-20 | 2020-12-25 | 2020-12-30 | Finalizado | Alice B. | 4 | 9600
PROJ-20-3003 | Manutenção Galpão | 372000 | 2020-01-10 | 2020-12-18 | 2020-12-30 | Finalizado | Bianca G. | 6 | 14400
PROJ-20-3004 | Manutenção Máquinas | 270000 | 2020-01-05 | 2020-12-18 | 2020-12-30 | Finalizado | Alice B. | 6 | 14400
PROJ-20-3005 | Manutenção Engrenagens | 336000 | 2020-01-05 | 2020-12-18 | 2020-12-30 | Finalizado | Bianca G. | 3 | 7200
PROJ-20-3006 | Manutenção de Softwares | 240000 | 2020-01-02 | 2020-12-18 | 2020-12-30 | Finalizado | Gustavo A. | 4 | 48000

## orcamento_projeto
Projeto | Descrição | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
PROJ-20-3000 | Manutenção Motores | 12400 | 6200 | 12400 | 31000 | 31000 | 62000 | 93000 | 124000 | 155000 | 49600 | 31000 | 12400
PROJ-20-3001 | Manutenção Paineis | 5000 | 10000 | 15000 | 50000 | 50000 | 75000 | 50000 | 90000 | 105000 | 35000 | 10000 | 5000
PROJ-20-3002 | Manutenção Embarcação | 50500 | 50500 | 10100 | 101000 | 202000 | 303000 | 121200 | 50500 | 50500 | 20200 | 20200 | 30300
PROJ-20-3003 | Manutenção Galpão | 7440 | 3720 | 7440 | 18600 | 18600 | 37200 | 55800 | 74400 | 93000 | 29760 | 18600 | 7440
PROJ-20-3004 | Manutenção Máquinas | 27000 | 13500 | 27000 | 54000 | 54000 | 40500 | 21600 | 13500 | 5400 | 5400 | 5400 | 2700
PROJ-20-3005 | Manutenção Engrenagens | 33600 | 16800 | 33600 | 67200 | 67200 | 50400 | 26880 | 16800 | 6720 | 6720 | 6720 | 3360
PROJ-20-3006 | Upgrade de Sistemas | 4800 | 2400 | 4800 | 12000 | 12000 | 24000 | 36000 | 48000 | 60000 | 19200 | 12000 | 4800

## custo_projeto
Período | Valor | Moeda | Descricao do Item | PROJETO | Classificação | Fornecedor
2020-01-01 | 15000 | BRL | ENGINE PARTs | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-02-01 | 4000 | BRL | ENGINE PARTs | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-03-01 | 20000 | BRL | ENGINE PARTs | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-04-01 | 50000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-05-01 | 50000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-06-01 | 120000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-07-01 | 10000 | BRL | Spare Parts | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-08-01 | 200000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-09-01 | 155000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-10-01 | 120000 | BRL | Panel Mounting and System Structure | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-01-01 | 4500 | BRL | Panel Mounting Structure | PROJ-20-3001 | MATERIAL | SOFTX COMPANY
2020-02-01 | 9000 | BRL | Local Labor | PROJ-20-3001 | SERVIÇO | LABOR
2020-03-01 | 13500 | BRL | Databook Registration | PROJ-20-3001 | OUTROS | HUSR Certification
2020-04-01 | 60000 | BRL | Onsite Survey | PROJ-20-3001 | MATERIAL | VESSEL D&A CO
2020-05-01 | 60000 | BRL | Equipment & Tools | PROJ-20-3001 | MATERIAL | VESSEL D&A CO
2020-06-01 | 67500 | BRL | Equipment & Tools | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-07-01 | 45000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-08-01 | 81000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-09-01 | 94500 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-10-01 | 31500 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-01-01 | 106050 | BRL | Materials and Spare | PROJ-20-3002 | MATERIAL | VESSEL D&A CO
2020-02-01 | 9000 | BRL | Survey | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-03-01 | 65000 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-04-01 | 106050 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-05-01 | 212100 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-06-01 | 293910 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-07-01 | 117564 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-08-01 | 48985 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-09-01 | 48985 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-10-01 | 9797 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-01-01 | 14880 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-02-01 | 18600 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-03-01 | 22320 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-04-01 | 33480 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-05-01 | 18600 | BRL | Spare Parts | PROJ-20-3003 | MATERIAL | SOFTX COMPANY
2020-06-01 | 37200 | BRL | Spare Parts | PROJ-20-3003 | MATERIAL | SOFTX COMPANY
2020-07-01 | 55800 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-08-01 | 74400 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-09-01 | 120000 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-10-01 | 29760 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-01-01 | 24300 | BRL | Materials and Spare | PROJ-20-3004 | MATERIAL | CAYG Engineering
2020-02-01 | 12150 | BRL | Materials and Spare | PROJ-20-3004 | MATERIAL | CAYG Engineering
2020-03-01 | 24300 | BRL | Materials and Spare | PROJ-20-3004 | MATERIAL | CAYG Engineering
2020-04-01 | 48600 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-05-01 | 48600 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-06-01 | 36450 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-07-01 | 19440 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-08-01 | 12150 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-09-01 | 4860 | BRL | Project Documentation | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-10-01 | 10000 | BRL | Project Documentation | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-01-01 | 30240 | BRL | ENGINE PARTs | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-02-01 | 15120 | BRL | ENGINE PARTs | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-03-01 | 30240 | BRL | ENGINE PARTs | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-04-01 | 60480 | BRL | General Maitenance | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-05-01 | 60480 | BRL | General Maitenance | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-06-01 | 45360 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-07-01 | 24192 | BRL | Spare Parts | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-08-01 | 15120 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-09-01 | 15120 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-10-01 | 7500 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | SOFTX COMPANY
2020-01-01 | 4896 | BRL | Onsite Survey | PROJ-20-3006 | SERVIÇO | REX POWER
2020-02-01 | 2448 | BRL | Onsite Survey | PROJ-20-3006 | SERVIÇO | REX POWER
2020-03-01 | 4896 | BRL | Onsite Survey | PROJ-20-3006 | SERVIÇO | REX POWER
2020-04-01 | 12240 | BRL | Equipment Manufacturing Tools | PROJ-20-3006 | MATERIAL | REX POWER
2020-05-01 | 12240 | BRL | Equipment Manufacturing Tools | PROJ-20-3006 | MATERIAL | REX POWER
2020-06-01 | 19200 | BRL | Equipment Manufacturing Tools | PROJ-20-3006 | MATERIAL | REX POWER
2020-07-01 | 28800 | BRL | Engineering Services | PROJ-20-3006 | SERVIÇO | REX POWER
2020-08-01 | 38400 | BRL | Engineering Services | PROJ-20-3006 | SERVIÇO | REX POWER
2020-09-01 | 48000 | BRL | Systems implementation | PROJ-20-3006 | SERVIÇO | REX POWER
2020-10-01 | 50000 | BRL | Systems implementation | PROJ-20-3006 | SERVIÇO | REX POWER
2020-11-01 | 5000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-12-01 | 10000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-12-01 | 9797 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-12-01 | 10000 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-12-01 | 5000 | BRL | Project Documentation | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-11-01 | 7500 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | SOFTX COMPANY
2020-12-01 | 10000 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | SOFTX COMPANY
2020-11-01 | 15000 | BRL | Systems implementation Report | PROJ-20-3006 | SERVIÇO | REX POWER

## calendario
data | mes | mes_num | semana
2020-01-01 | jan | 1 | qua
2020-01-02 | jan | 1 | qui
2020-01-03 | jan | 1 | sex
2020-01-04 | jan | 1 | sáb
2020-01-05 | jan | 1 | dom
2020-01-06 | jan | 1 | seg
2020-01-07 | jan | 1 | ter
2020-01-08 | jan | 1 | qua
2020-01-09 | jan | 1 | qui
2020-01-10 | jan | 1 | sex
2020-01-11 | jan | 1 | sáb
2020-01-12 | jan | 1 | dom
2020-01-13 | jan | 1 | seg
2020-01-14 | jan | 1 | ter
2020-01-15 | jan | 1 | qua
2020-01-16 | jan | 1 | qui
2020-01-17 | jan | 1 | sex
2020-01-18 | jan | 1 | sáb
2020-01-19 | jan | 1 | dom
2020-01-20 | jan | 1 | seg
2020-01-21 | jan | 1 | ter
2020-01-22 | jan | 1 | qua
2020-01-23 | jan | 1 | qui
2020-01-24 | jan | 1 | sex
2020-01-25 | jan | 1 | sáb
2020-01-26 | jan | 1 | dom
2020-01-27 | jan | 1 | seg
2020-01-28 | jan | 1 | ter
2020-01-29 | jan | 1 | qua
2020-01-30 | jan | 1 | qui
2020-01-31 | jan | 1 | sex
2020-02-01 | fev | 2 | sáb
2020-02-02 | fev | 2 | dom
2020-02-03 | fev | 2 | seg
2020-02-04 | fev | 2 | ter
2020-02-05 | fev | 2 | qua
2020-02-06 | fev | 2 | qui
2020-02-07 | fev | 2 | sex
2020-02-08 | fev | 2 | sáb
2020-02-09 | fev | 2 | dom
2020-02-10 | fev | 2 | seg
2020-02-11 | fev | 2 | ter
2020-02-12 | fev | 2 | qua
2020-02-13 | fev | 2 | qui
2020-02-14 | fev | 2 | sex
2020-02-15 | fev | 2 | sáb
2020-02-16 | fev | 2 | dom
2020-02-17 | fev | 2 | seg
2020-02-18 | fev | 2 | ter
2020-02-19 | fev | 2 | qua
2020-02-20 | fev | 2 | qui
2020-02-21 | fev | 2 | sex
2020-02-22 | fev | 2 | sáb
2020-02-23 | fev | 2 | dom
2020-02-24 | fev | 2 | seg
2020-02-25 | fev | 2 | ter
2020-02-26 | fev | 2 | qua
2020-02-27 | fev | 2 | qui
2020-02-28 | fev | 2 | sex
2020-02-29 | fev | 2 | sáb
2020-03-01 | mar | 3 | dom
2020-03-02 | mar | 3 | seg
2020-03-03 | mar | 3 | ter
2020-03-04 | mar | 3 | qua
2020-03-05 | mar | 3 | qui
2020-03-06 | mar | 3 | sex
2020-03-07 | mar | 3 | sáb
2020-03-08 | mar | 3 | dom
2020-03-09 | mar | 3 | seg
2020-03-10 | mar | 3 | ter
2020-03-11 | mar | 3 | qua
2020-03-12 | mar | 3 | qui
2020-03-13 | mar | 3 | sex
2020-03-14 | mar | 3 | sáb
2020-03-15 | mar | 3 | dom
2020-03-16 | mar | 3 | seg
2020-03-17 | mar | 3 | ter
2020-03-18 | mar | 3 | qua
2020-03-19 | mar | 3 | qui
2020-03-20 | mar | 3 | sex
2020-03-21 | mar | 3 | sáb
2020-03-22 | mar | 3 | dom
2020-03-23 | mar | 3 | seg
2020-03-24 | mar | 3 | ter
2020-03-25 | mar | 3 | qua
2020-03-26 | mar | 3 | qui
2020-03-27 | mar | 3 | sex
2020-03-28 | mar | 3 | sáb
2020-03-29 | mar | 3 | dom
2020-03-30 | mar | 3 | seg
2020-03-31 | mar | 3 | ter
2020-04-01 | abr | 4 | qua
2020-04-02 | abr | 4 | qui
2020-04-03 | abr | 4 | sex
2020-04-04 | abr | 4 | sáb
2020-04-05 | abr | 4 | dom
2020-04-06 | abr | 4 | seg
2020-04-07 | abr | 4 | ter
2020-04-08 | abr | 4 | qua
2020-04-09 | abr | 4 | qui
2020-04-10 | abr | 4 | sex
2020-04-11 | abr | 4 | sáb
2020-04-12 | abr | 4 | dom
2020-04-13 | abr | 4 | seg
2020-04-14 | abr | 4 | ter
2020-04-15 | abr | 4 | qua
2020-04-16 | abr | 4 | qui
2020-04-17 | abr | 4 | sex
2020-04-18 | abr | 4 | sáb
2020-04-19 | abr | 4 | dom
2020-04-20 | abr | 4 | seg
2020-04-21 | abr | 4 | ter
2020-04-22 | abr | 4 | qua
2020-04-23 | abr | 4 | qui
2020-04-24 | abr | 4 | sex
2020-04-25 | abr | 4 | sáb
2020-04-26 | abr | 4 | dom
2020-04-27 | abr | 4 | seg
2020-04-28 | abr | 4 | ter
2020-04-29 | abr | 4 | qua
2020-04-30 | abr | 4 | qui
2020-05-01 | mai | 5 | sex
2020-05-02 | mai | 5 | sáb
2020-05-03 | mai | 5 | dom
2020-05-04 | mai | 5 | seg
2020-05-05 | mai | 5 | ter
2020-05-06 | mai | 5 | qua
2020-05-07 | mai | 5 | qui
2020-05-08 | mai | 5 | sex
2020-05-09 | mai | 5 | sáb
2020-05-10 | mai | 5 | dom
2020-05-11 | mai | 5 | seg
2020-05-12 | mai | 5 | ter
2020-05-13 | mai | 5 | qua
2020-05-14 | mai | 5 | qui
2020-05-15 | mai | 5 | sex
2020-05-16 | mai | 5 | sáb
2020-05-17 | mai | 5 | dom
2020-05-18 | mai | 5 | seg
2020-05-19 | mai | 5 | ter
2020-05-20 | mai | 5 | qua
2020-05-21 | mai | 5 | qui
2020-05-22 | mai | 5 | sex
2020-05-23 | mai | 5 | sáb
2020-05-24 | mai | 5 | dom
2020-05-25 | mai | 5 | seg
2020-05-26 | mai | 5 | ter
2020-05-27 | mai | 5 | qua
2020-05-28 | mai | 5 | qui
2020-05-29 | mai | 5 | sex
2020-05-30 | mai | 5 | sáb
2020-05-31 | mai | 5 | dom
2020-06-01 | jun | 6 | seg
2020-06-02 | jun | 6 | ter
2020-06-03 | jun | 6 | qua
2020-06-04 | jun | 6 | qui
2020-06-05 | jun | 6 | sex
2020-06-06 | jun | 6 | sáb
2020-06-07 | jun | 6 | dom
2020-06-08 | jun | 6 | seg
2020-06-09 | jun | 6 | ter
2020-06-10 | jun | 6 | qua
2020-06-11 | jun | 6 | qui
2020-06-12 | jun | 6 | sex
2020-06-13 | jun | 6 | sáb
2020-06-14 | jun | 6 | dom
2020-06-15 | jun | 6 | seg
2020-06-16 | jun | 6 | ter
2020-06-17 | jun | 6 | qua
2020-06-18 | jun | 6 | qui
2020-06-19 | jun | 6 | sex
2020-06-20 | jun | 6 | sáb
2020-06-21 | jun | 6 | dom
2020-06-22 | jun | 6 | seg
2020-06-23 | jun | 6 | ter
2020-06-24 | jun | 6 | qua
2020-06-25 | jun | 6 | qui
2020-06-26 | jun | 6 | sex
2020-06-27 | jun | 6 | sáb
2020-06-28 | jun | 6 | dom
2020-06-29 | jun | 6 | seg
2020-06-30 | jun | 6 | ter
2020-07-01 | jul | 7 | qua
2020-07-02 | jul | 7 | qui
2020-07-03 | jul | 7 | sex
2020-07-04 | jul | 7 | sáb
2020-07-05 | jul | 7 | dom
2020-07-06 | jul | 7 | seg
2020-07-07 | jul | 7 | ter
2020-07-08 | jul | 7 | qua
2020-07-09 | jul | 7 | qui
2020-07-10 | jul | 7 | sex
2020-07-11 | jul | 7 | sáb
2020-07-12 | jul | 7 | dom
2020-07-13 | jul | 7 | seg
2020-07-14 | jul | 7 | ter
2020-07-15 | jul | 7 | qua
2020-07-16 | jul | 7 | qui
2020-07-17 | jul | 7 | sex
2020-07-18 | jul | 7 | sáb
2020-07-19 | jul | 7 | dom
2020-07-20 | jul | 7 | seg
2020-07-21 | jul | 7 | ter
2020-07-22 | jul | 7 | qua
2020-07-23 | jul | 7 | qui
2020-07-24 | jul | 7 | sex
2020-07-25 | jul | 7 | sáb
2020-07-26 | jul | 7 | dom
2020-07-27 | jul | 7 | seg
2020-07-28 | jul | 7 | ter
2020-07-29 | jul | 7 | qua
2020-07-30 | jul | 7 | qui
2020-07-31 | jul | 7 | sex
2020-08-01 | ago | 8 | sáb
2020-08-02 | ago | 8 | dom
2020-08-03 | ago | 8 | seg
2020-08-04 | ago | 8 | ter
2020-08-05 | ago | 8 | qua
2020-08-06 | ago | 8 | qui
2020-08-07 | ago | 8 | sex
2020-08-08 | ago | 8 | sáb
2020-08-09 | ago | 8 | dom
2020-08-10 | ago | 8 | seg
2020-08-11 | ago | 8 | ter
2020-08-12 | ago | 8 | qua
2020-08-13 | ago | 8 | qui
2020-08-14 | ago | 8 | sex
2020-08-15 | ago | 8 | sáb
2020-08-16 | ago | 8 | dom
2020-08-17 | ago | 8 | seg
2020-08-18 | ago | 8 | ter
2020-08-19 | ago | 8 | qua
2020-08-20 | ago | 8 | qui
2020-08-21 | ago | 8 | sex
2020-08-22 | ago | 8 | sáb
2020-08-23 | ago | 8 | dom
2020-08-24 | ago | 8 | seg
2020-08-25 | ago | 8 | ter
2020-08-26 | ago | 8 | qua
2020-08-27 | ago | 8 | qui
2020-08-28 | ago | 8 | sex
2020-08-29 | ago | 8 | sáb
2020-08-30 | ago | 8 | dom
2020-08-31 | ago | 8 | seg
2020-09-01 | set | 9 | ter
2020-09-02 | set | 9 | qua
2020-09-03 | set | 9 | qui
2020-09-04 | set | 9 | sex
2020-09-05 | set | 9 | sáb
2020-09-06 | set | 9 | dom
2020-09-07 | set | 9 | seg
2020-09-08 | set | 9 | ter
2020-09-09 | set | 9 | qua
2020-09-10 | set | 9 | qui
2020-09-11 | set | 9 | sex
2020-09-12 | set | 9 | sáb
2020-09-13 | set | 9 | dom
2020-09-14 | set | 9 | seg
2020-09-15 | set | 9 | ter
2020-09-16 | set | 9 | qua
2020-09-17 | set | 9 | qui
2020-09-18 | set | 9 | sex
2020-09-19 | set | 9 | sáb
2020-09-20 | set | 9 | dom
2020-09-21 | set | 9 | seg
2020-09-22 | set | 9 | ter
2020-09-23 | set | 9 | qua
2020-09-24 | set | 9 | qui
2020-09-25 | set | 9 | sex
2020-09-26 | set | 9 | sáb
2020-09-27 | set | 9 | dom
2020-09-28 | set | 9 | seg
2020-09-29 | set | 9 | ter
2020-09-30 | set | 9 | qua
2020-10-01 | out | 10 | qui
2020-10-02 | out | 10 | sex
2020-10-03 | out | 10 | sáb
2020-10-04 | out | 10 | dom
2020-10-05 | out | 10 | seg
2020-10-06 | out | 10 | ter
2020-10-07 | out | 10 | qua
2020-10-08 | out | 10 | qui
2020-10-09 | out | 10 | sex
2020-10-10 | out | 10 | sáb
2020-10-11 | out | 10 | dom
2020-10-12 | out | 10 | seg
2020-10-13 | out | 10 | ter
2020-10-14 | out | 10 | qua
2020-10-15 | out | 10 | qui
2020-10-16 | out | 10 | sex
2020-10-17 | out | 10 | sáb
2020-10-18 | out | 10 | dom
2020-10-19 | out | 10 | seg
2020-10-20 | out | 10 | ter
2020-10-21 | out | 10 | qua
2020-10-22 | out | 10 | qui
2020-10-23 | out | 10 | sex
2020-10-24 | out | 10 | sáb
2020-10-25 | out | 10 | dom
2020-10-26 | out | 10 | seg
2020-10-27 | out | 10 | ter
2020-10-28 | out | 10 | qua
2020-10-29 | out | 10 | qui
2020-10-30 | out | 10 | sex
2020-10-31 | out | 10 | sáb
2020-11-01 | nov | 11 | dom
2020-11-02 | nov | 11 | seg
2020-11-03 | nov | 11 | ter
2020-11-04 | nov | 11 | qua
2020-11-05 | nov | 11 | qui
2020-11-06 | nov | 11 | sex
2020-11-07 | nov | 11 | sáb
2020-11-08 | nov | 11 | dom
2020-11-09 | nov | 11 | seg
2020-11-10 | nov | 11 | ter
2020-11-11 | nov | 11 | qua
2020-11-12 | nov | 11 | qui
2020-11-13 | nov | 11 | sex
2020-11-14 | nov | 11 | sáb
2020-11-15 | nov | 11 | dom
2020-11-16 | nov | 11 | seg
2020-11-17 | nov | 11 | ter
2020-11-18 | nov | 11 | qua
2020-11-19 | nov | 11 | qui
2020-11-20 | nov | 11 | sex
2020-11-21 | nov | 11 | sáb
2020-11-22 | nov | 11 | dom
2020-11-23 | nov | 11 | seg
2020-11-24 | nov | 11 | ter
2020-11-25 | nov | 11 | qua
2020-11-26 | nov | 11 | qui
2020-11-27 | nov | 11 | sex
2020-11-28 | nov | 11 | sáb
2020-11-29 | nov | 11 | dom
2020-11-30 | nov | 11 | seg
2020-12-01 | dez | 12 | ter
2020-12-02 | dez | 12 | qua
2020-12-03 | dez | 12 | qui
2020-12-04 | dez | 12 | sex
2020-12-05 | dez | 12 | sáb
2020-12-06 | dez | 12 | dom
2020-12-07 | dez | 12 | seg
2020-12-08 | dez | 12 | ter
2020-12-09 | dez | 12 | qua
2020-12-10 | dez | 12 | qui
2020-12-11 | dez | 12 | sex
2020-12-12 | dez | 12 | sáb
2020-12-13 | dez | 12 | dom
2020-12-14 | dez | 12 | seg
2020-12-15 | dez | 12 | ter
2020-12-16 | dez | 12 | qua
2020-12-17 | dez | 12 | qui
2020-12-18 | dez | 12 | sex
2020-12-19 | dez | 12 | sáb
2020-12-20 | dez | 12 | dom
2020-12-21 | dez | 12 | seg
2020-12-22 | dez | 12 | ter
2020-12-23 | dez | 12 | qua
2020-12-24 | dez | 12 | qui
2020-12-25 | dez | 12 | sex
2020-12-26 | dez | 12 | sáb
2020-12-27 | dez | 12 | dom
2020-12-28 | dez | 12 | seg
2020-12-29 | dez | 12 | ter
2020-12-30 | dez | 12 | qua
2020-12-31 | dez | 12 | qui